## Summary
Month | 2017-04-01
Section | Section Name | Item | Item Name | Suma de Plan Local2 | Suma de Forecast Local2
A | NuevaUnión - Key Decisions |  |  | 7.911% | 6.713%
B | Baseline gathering, monitoring and similar |  |  | 0.8% | 0.8%
C | Fluor engineering and NU's input for EIA |  |  | 21.66% | 13.42%
D | EIA Development (Assembly by KP) |  |  | 1.735% | 1.735%
EIA Progress |  |  |  | 32.11% | 22.67%

## DB Items
Progress | Section | Section Name | Item | Item Name | Month | Plan Local | Forecast Local | Section Weight | Item Weight | Plan Local | Forecast Local
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-05-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-06-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-07-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-08-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-09-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-10-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-11-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-12-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-01-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-02-01 | 9.901% | 7.985% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-03-01 | 68.3% | 58.46% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-04-01 | 79.11% | 67.13% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-05-01 | 87.76% | 71.19% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-06-01 | 95.36% | 82.99% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-07-01 | 100% | 97.69% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-08-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-09-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-10-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-11-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-12-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-01-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-02-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-03-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-04-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-05-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-06-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-07-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-08-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-09-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-10-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-11-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-12-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-02-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-03-01 | 100% | 95% | 10% | 10% | 1% | 0.95%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A1 | Fast Flitering | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-02-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-03-01 | 100% | 95% | 10% | 10% | 1% | 0.95%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A2 | Desalination Plant | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-02-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-03-01 | 22.73% | 12.82% | 10% | 10% | 0.2273% | 0.1282%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-04-01 | 68.18% | 38.46% | 10% | 10% | 0.6818% | 0.3846%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-05-01 | 100% | 38.46% | 10% | 10% | 1% | 0.3846%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-06-01 | 100% | 38.46% | 10% | 10% | 1% | 0.3846%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-07-01 | 100% | 76.92% | 10% | 10% | 1% | 0.7692%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A3 | Port | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-02-01 | 17.86% | 17.86% | 10% | 10% | 0.1786% | 0.1786%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-03-01 | 89.29% | 89.29% | 10% | 10% | 0.8929% | 0.8929%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A4 | Concentrate Transport | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-02-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-03-01 | 88.89% | 88.89% | 10% | 10% | 0.8889% | 0.8889%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A5 | Rockfill 1 vs 2 | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-02-01 | 17.86% | 17.86% | 10% | 10% | 0.1786% | 0.1786%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-03-01 | 89.29% | 89.29% | 10% | 10% | 0.8929% | 0.8929%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-04-01 | 100% | 89.29% | 10% | 10% | 1% | 0.8929%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A6 | Power Transmission | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-02-01 | 33.33% | 12.82% | 10% | 10% | 0.3333% | 0.1282%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-03-01 | 100% | 25.64% | 10% | 10% | 1% | 0.2564%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-04-01 | 100% | 38.46% | 10% | 10% | 1% | 0.3846%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-05-01 | 100% | 38.46% | 10% | 10% | 1% | 0.3846%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-06-01 | 100% | 64.1% | 10% | 10% | 1% | 0.641%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A7 | Water for Construction | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-02-01 | 15.04% | 16.39% | 10% | 10% | 0.1504% | 0.1639%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-03-01 | 45.11% | 40.98% | 10% | 10% | 0.4511% | 0.4098%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-04-01 | 75.19% | 57.38% | 10% | 10% | 0.7519% | 0.5738%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-05-01 | 100% | 57.38% | 10% | 10% | 1% | 0.5738%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-06-01 | 100% | 73.77% | 10% | 10% | 1% | 0.7377%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A8 | HPGR | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-02-01 | 14.93% | 14.93% | 10% | 10% | 0.1493% | 0.1493%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-03-01 | 29.85% | 29.85% | 10% | 10% | 0.2985% | 0.2985%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-04-01 | 29.85% | 29.85% | 10% | 10% | 0.2985% | 0.2985%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-05-01 | 59.7% | 59.7% | 10% | 10% | 0.597% | 0.597%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A9 | Camp Strategy | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-05-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-06-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-07-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-08-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-09-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-10-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-11-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2016-12-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-01-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-02-01 | 0% | 0% | 10% | 10% | 0% | 0%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-03-01 | 17.86% | 17.86% | 10% | 10% | 0.1786% | 0.1786%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-04-01 | 17.86% | 17.86% | 10% | 10% | 0.1786% | 0.1786%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-05-01 | 17.86% | 17.86% | 10% | 10% | 0.1786% | 0.1786%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-06-01 | 53.57% | 53.57% | 10% | 10% | 0.5357% | 0.5357%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2017-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-01-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-02-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-03-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-04-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-05-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-06-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-07-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-08-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-09-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-10-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-11-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | A | NuevaUnión - Key Decisions | A10 | Autonomous Trucking | 2018-12-01 | 100% | 100% | 10% | 10% | 1% | 1%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-05-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-06-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-07-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-08-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-09-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-10-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-11-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-12-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-01-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-02-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-03-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-04-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-05-01 | 38.5% | 38.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-06-01 | 41% | 41% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-07-01 | 43.5% | 43.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-08-01 | 50% | 50% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-09-01 | 52.5% | 52.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-10-01 | 55% | 55% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-11-01 | 57.5% | 57.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-12-01 | 60% | 60% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-01-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-02-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-03-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-04-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-05-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-06-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-07-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-08-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-09-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-10-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-11-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-12-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-05-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-06-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-07-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-08-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-09-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-10-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-11-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2016-12-01 | 0% | 0% | 20% | 80% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-01-01 | 5% | 5% | 20% | 80% | 0.8% | 0.8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-02-01 | 5% | 5% | 20% | 80% | 0.8% | 0.8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-03-01 | 5% | 5% | 20% | 80% | 0.8% | 0.8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-04-01 | 5% | 5% | 20% | 80% | 0.8% | 0.8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-05-01 | 45% | 45% | 20% | 80% | 7.2% | 7.2%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-06-01 | 45% | 45% | 20% | 80% | 7.2% | 7.2%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-07-01 | 45% | 45% | 20% | 80% | 7.2% | 7.2%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-08-01 | 50% | 50% | 20% | 80% | 8% | 8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-09-01 | 50% | 50% | 20% | 80% | 8% | 8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-10-01 | 50% | 50% | 20% | 80% | 8% | 8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-11-01 | 50% | 50% | 20% | 80% | 8% | 8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2017-12-01 | 50% | 50% | 20% | 80% | 8% | 8%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-01-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-02-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-03-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-04-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-05-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-06-01 | 90% | 90% | 20% | 80% | 14.4% | 14.4%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-07-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-08-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-09-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-10-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-11-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B1 | KP | 2018-12-01 | 100% | 100% | 20% | 80% | 16% | 16%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-05-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-06-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-07-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-08-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-09-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-10-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-11-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2016-12-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-01-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-02-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-03-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-04-01 | 0% | 0% | 20% | 20% | 0% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-05-01 | 12.5% | 0% | 20% | 20% | 0.5% | 0%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-06-01 | 25% | 14.29% | 20% | 20% | 1% | 0.5714%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-07-01 | 37.5% | 28.57% | 20% | 20% | 1.5% | 1.143%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-08-01 | 50% | 42.86% | 20% | 20% | 2% | 1.714%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-09-01 | 62.5% | 57.14% | 20% | 20% | 2.5% | 2.286%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-10-01 | 75% | 71.43% | 20% | 20% | 3% | 2.857%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-11-01 | 87.5% | 85.71% | 20% | 20% | 3.5% | 3.429%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2017-12-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-01-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-02-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-03-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-04-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-05-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-06-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-07-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-08-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-09-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-10-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-11-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | B | Baseline gathering, monitoring and similar | B2 | Monitoring | 2018-12-01 | 100% | 100% | 20% | 20% | 4% | 4%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-05-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-06-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-07-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-08-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-09-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-10-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-11-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-12-01 | 0.8505% | 0.9309% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-01-01 | 1.998% | 2.467% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-02-01 | 6.652% | 5.914% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-03-01 | 23.31% | 21.84% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-04-01 | 61.9% | 38.35% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-05-01 | 79.97% | 69.88% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-06-01 | 93.5% | 84.68% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-07-01 | 99.74% | 97.14% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-08-01 | 99.74% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-09-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-10-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-11-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-12-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-01-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-02-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-03-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-04-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-05-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-06-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-07-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-08-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-09-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-10-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-11-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-12-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-05-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-06-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-07-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-08-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-09-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-10-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-11-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2016-12-01 | 0.5636% | 0.5636% | 35% | 14% | 0.02762% | 0.02762%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-01-01 | 3.251% | 3.251% | 35% | 14% | 0.1593% | 0.1593%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-02-01 | 15.69% | 15.69% | 35% | 14% | 0.7688% | 0.7688%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-03-01 | 39.03% | 39.03% | 35% | 14% | 1.912% | 1.912%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-04-01 | 61.98% | 61.98% | 35% | 14% | 3.037% | 3.037%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-05-01 | 83.52% | 83.52% | 35% | 14% | 4.092% | 4.092%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-06-01 | 97.82% | 97.82% | 35% | 14% | 4.793% | 4.793%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-07-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-08-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-09-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-10-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-11-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2017-12-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-01-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-02-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-03-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-04-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-05-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-06-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-07-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-08-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-09-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-10-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-11-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C1 | Fluor Off-Shore | 2018-12-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-05-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-06-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-07-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-08-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-09-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-10-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-11-01 | 0% | 0% | 35% | 34% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2016-12-01 | 2.269% | 2.506% | 35% | 34% | 0.2701% | 0.2982%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-01-01 | 4.539% | 5.918% | 35% | 34% | 0.5401% | 0.7042%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-02-01 | 8.019% | 8.339% | 35% | 34% | 0.9542% | 0.9923%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-03-01 | 21.18% | 21.72% | 35% | 34% | 2.52% | 2.585%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-04-01 | 45.8% | 35.9% | 35% | 34% | 5.45% | 4.272%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-05-01 | 69.84% | 56.54% | 35% | 34% | 8.311% | 6.728%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-06-01 | 85.63% | 74.74% | 35% | 34% | 10.19% | 8.894%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-07-01 | 99.24% | 91.58% | 35% | 34% | 11.81% | 10.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-08-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-09-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-10-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-11-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2017-12-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-01-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-02-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-03-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-04-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-05-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-06-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-07-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-08-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-09-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-10-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-11-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C2 | Fluor On-Shore | 2018-12-01 | 100% | 100% | 35% | 34% | 11.9% | 11.9%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-05-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-06-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-07-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-08-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-09-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-10-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-11-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2016-12-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-01-01 | 0% | 0% | 35% | 29% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-02-01 | 5.961% | 3.041% | 35% | 29% | 0.605% | 0.3087%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-03-01 | 36.7% | 31% | 35% | 29% | 3.725% | 3.147%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-04-01 | 55.88% | 51.67% | 35% | 29% | 5.672% | 5.244%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-05-01 | 79.62% | 75.93% | 35% | 29% | 8.082% | 7.707%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-06-01 | 100% | 97.85% | 35% | 29% | 10.15% | 9.932%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-07-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-08-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-09-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-10-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-11-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2017-12-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-01-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-02-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-03-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-04-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-05-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-06-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-07-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-08-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-09-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-10-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-11-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C3 | Fluor 3rd party | 2018-12-01 | 100% | 100% | 35% | 29% | 10.15% | 10.15%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-05-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-06-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-07-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-08-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-09-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-10-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-11-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2016-12-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-01-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-02-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-03-01 | 0% | 0% | 35% | 14% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-04-01 | 88.89% | 17.78% | 35% | 14% | 4.356% | 0.8711%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-05-01 | 88.89% | 88.89% | 35% | 14% | 4.356% | 4.356%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-06-01 | 90.67% | 90.67% | 35% | 14% | 4.443% | 4.443%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-07-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-08-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-09-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-10-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-11-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2017-12-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-01-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-02-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-03-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-04-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-05-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-06-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-07-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-08-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-09-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-10-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-11-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C4 | NU-Operations (mining focus) | 2018-12-01 | 100% | 100% | 35% | 14% | 4.9% | 4.9%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-05-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-06-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-07-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-08-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-09-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-10-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-11-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2016-12-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-01-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-02-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-03-01 | 0% | 0% | 35% | 9% | 0% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-04-01 | 100% | 0% | 35% | 9% | 3.15% | 0%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-05-01 | 100% | 50% | 35% | 9% | 3.15% | 1.575%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-06-01 | 100% | 50% | 35% | 9% | 3.15% | 1.575%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-07-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-08-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-09-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-10-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-11-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2017-12-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-01-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-02-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-03-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-04-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-05-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-06-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-07-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-08-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-09-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-10-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-11-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | C | Fluor engineering and NU's input for EIA | C5 | Piteau | 2018-12-01 | 100% | 100% | 35% | 9% | 3.15% | 3.15%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-05-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-06-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-07-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-08-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-09-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-10-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-11-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-12-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-01-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-02-01 | 1.774% | 1.774% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-03-01 | 2.844% | 2.844% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-04-01 | 4.956% | 4.956% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-05-01 | 7.537% | 7.537% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-06-01 | 11.83% | 11.83% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-07-01 | 15.3% | 15.3% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-08-01 | 21.7% | 21.7% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-09-01 | 29.69% | 29.69% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-10-01 | 33.2% | 33.2% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-11-01 | 36.57% | 36.57% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-12-01 | 68% | 76.62% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-01-01 | 77.46% | 77.81% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-02-01 | 78.51% | 78.86% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-03-01 | 79.35% | 92.12% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-04-01 | 92.97% | 92.97% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-05-01 | 92.97% | 94.53% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-06-01 | 93.76% | 95.32% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-07-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-08-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-09-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-10-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-11-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-12-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-05-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-06-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-07-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-08-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-09-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-10-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-11-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2016-12-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-01-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-02-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-03-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-04-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-05-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-06-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-07-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-08-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-09-01 | 35% | 35% | 35% | 10% | 1.225% | 1.225%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-10-01 | 35% | 35% | 35% | 10% | 1.225% | 1.225%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-11-01 | 35% | 35% | 35% | 10% | 1.225% | 1.225%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2017-12-01 | 80% | 80% | 35% | 10% | 2.8% | 2.8%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-01-01 | 80% | 80% | 35% | 10% | 2.8% | 2.8%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-02-01 | 80% | 80% | 35% | 10% | 2.8% | 2.8%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-03-01 | 80% | 90% | 35% | 10% | 2.8% | 3.15%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-04-01 | 90% | 90% | 35% | 10% | 3.15% | 3.15%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-05-01 | 90% | 90% | 35% | 10% | 3.15% | 3.15%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-06-01 | 90% | 90% | 35% | 10% | 3.15% | 3.15%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-07-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-08-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-09-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-10-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-11-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D1 | Project Description | 2018-12-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-05-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-06-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-07-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-08-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-09-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-10-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-11-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2016-12-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-01-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-02-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-03-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-04-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-05-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-06-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-07-01 | 0% | 0% | 35% | 40% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-08-01 | 6.897% | 6.897% | 35% | 40% | 0.9655% | 0.9655%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-09-01 | 6.897% | 6.897% | 35% | 40% | 0.9655% | 0.9655%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-10-01 | 6.897% | 6.897% | 35% | 40% | 0.9655% | 0.9655%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-11-01 | 6.897% | 6.897% | 35% | 40% | 0.9655% | 0.9655%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2017-12-01 | 51.15% | 71.84% | 35% | 40% | 7.161% | 10.06%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-01-01 | 71.84% | 72.3% | 35% | 40% | 10.06% | 10.12%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-02-01 | 71.84% | 72.3% | 35% | 40% | 10.06% | 10.12%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-03-01 | 71.84% | 90% | 35% | 40% | 10.06% | 12.6%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-04-01 | 90% | 90% | 35% | 40% | 12.6% | 12.6%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-05-01 | 90% | 91.84% | 35% | 40% | 12.6% | 12.86%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-06-01 | 90% | 91.84% | 35% | 40% | 12.6% | 12.86%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-07-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-08-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-09-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-10-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-11-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D2 | Calculation of impacts, measures & monitoring | 2018-12-01 | 100% | 100% | 35% | 40% | 14% | 14%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-05-01 | 0% | 0% | 35% | 16% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-06-01 | 0% | 0% | 35% | 16% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-07-01 | 0% | 0% | 35% | 16% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-08-01 | 0% | 0% | 35% | 16% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-09-01 | 0% | 0% | 35% | 16% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-10-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-11-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2016-12-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-01-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-02-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-03-01 | 9.524% | 9.524% | 35% | 16% | 0.5333% | 0.5333%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-04-01 | 14.29% | 14.29% | 35% | 16% | 0.8% | 0.8%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-05-01 | 17.14% | 17.14% | 35% | 16% | 0.96% | 0.96%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-06-01 | 27.14% | 27.14% | 35% | 16% | 1.52% | 1.52%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-07-01 | 27.14% | 27.14% | 35% | 16% | 1.52% | 1.52%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-08-01 | 36.67% | 36.67% | 35% | 16% | 2.053% | 2.053%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-09-01 | 36.67% | 36.67% | 35% | 16% | 2.053% | 2.053%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-10-01 | 36.67% | 36.67% | 35% | 16% | 2.053% | 2.053%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-11-01 | 46.19% | 46.19% | 35% | 16% | 2.587% | 2.587%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2017-12-01 | 64.05% | 64.05% | 35% | 16% | 3.587% | 3.587%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-01-01 | 64.05% | 65% | 35% | 16% | 3.587% | 3.64%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-02-01 | 64.05% | 65% | 35% | 16% | 3.587% | 3.64%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-03-01 | 64.05% | 89.05% | 35% | 16% | 3.587% | 4.987%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-04-01 | 89.05% | 89.05% | 35% | 16% | 4.987% | 4.987%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-05-01 | 89.05% | 93.81% | 35% | 16% | 4.987% | 5.253%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-06-01 | 93.81% | 98.57% | 35% | 16% | 5.253% | 5.52%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-07-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-08-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-09-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-10-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-11-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D3 | Other Chapters of EIA report (PACA/PACI, monitoring plan , contingence, legal, PAS) | 2018-12-01 | 100% | 100% | 35% | 16% | 5.6% | 5.6%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-05-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-06-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-07-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-08-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-09-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-10-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-11-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2016-12-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-01-01 | 0% | 0% | 35% | 10% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-02-01 | 2.5% | 2.5% | 35% | 10% | 0.0875% | 0.0875%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-03-01 | 2.5% | 2.5% | 35% | 10% | 0.0875% | 0.0875%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-04-01 | 2.5% | 2.5% | 35% | 10% | 0.0875% | 0.0875%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-05-01 | 2.5% | 2.5% | 35% | 10% | 0.0875% | 0.0875%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-06-01 | 7.5% | 7.5% | 35% | 10% | 0.2625% | 0.2625%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-07-01 | 12.5% | 12.5% | 35% | 10% | 0.4375% | 0.4375%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-08-01 | 15% | 15% | 35% | 10% | 0.525% | 0.525%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-09-01 | 32.5% | 32.5% | 35% | 10% | 1.137% | 1.137%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-10-01 | 50% | 50% | 35% | 10% | 1.75% | 1.75%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-11-01 | 55% | 55% | 35% | 10% | 1.925% | 1.925%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2017-12-01 | 94% | 94% | 35% | 10% | 3.29% | 3.29%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-01-01 | 94% | 94% | 35% | 10% | 3.29% | 3.29%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-02-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-03-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-04-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-05-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-06-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-07-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-08-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-09-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-10-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-11-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D4 | Other Environmental Subcontratos (Geobiota, Amawta, etc.) | 2018-12-01 | 100% | 100% | 35% | 10% | 3.5% | 3.5%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-05-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-06-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-07-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-08-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-09-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-10-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-11-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2016-12-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-01-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-02-01 | 0% | 0% | 35% | 20% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-03-01 | 5.051% | 5.051% | 35% | 20% | 0.3535% | 0.3535%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-04-01 | 11.11% | 11.11% | 35% | 20% | 0.7778% | 0.7778%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-05-01 | 21.21% | 21.21% | 35% | 20% | 1.485% | 1.485%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-06-01 | 31.31% | 31.31% | 35% | 20% | 2.192% | 2.192%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-07-01 | 45.45% | 45.45% | 35% | 20% | 3.182% | 3.182%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-08-01 | 53.54% | 53.54% | 35% | 20% | 3.747% | 3.747%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-09-01 | 65.66% | 65.66% | 35% | 20% | 4.596% | 4.596%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-10-01 | 73.74% | 73.74% | 35% | 20% | 5.162% | 5.162%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-11-01 | 79.8% | 79.8% | 35% | 20% | 5.586% | 5.586%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2017-12-01 | 85.86% | 85.86% | 35% | 20% | 6.01% | 6.01%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-01-01 | 89.9% | 89.9% | 35% | 20% | 6.293% | 6.293%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-02-01 | 91.92% | 91.92% | 35% | 20% | 6.434% | 6.434%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-03-01 | 95.96% | 95.96% | 35% | 20% | 6.717% | 6.717%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-04-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-05-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-06-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-07-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-08-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-09-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-10-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-11-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D5 | RC/ Replan - Ressetlement Plan | 2018-12-01 | 100% | 100% | 35% | 20% | 7% | 7%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-05-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-06-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-07-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-08-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-09-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-10-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-11-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2016-12-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-01-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-02-01 | 0% | 0% | 35% | 4% | 0% | 0%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-03-01 | 1.5% | 1.5% | 35% | 4% | 0.021% | 0.021%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-04-01 | 4.956% | 4.956% | 35% | 4% | 0.06939% | 0.06939%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-05-01 | 7.537% | 7.537% | 35% | 4% | 0.1055% | 0.1055%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-06-01 | 11.83% | 11.83% | 35% | 4% | 0.1656% | 0.1656%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-07-01 | 15.3% | 15.3% | 35% | 4% | 0.2141% | 0.2141%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-08-01 | 21.7% | 21.7% | 35% | 4% | 0.3038% | 0.3038%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-09-01 | 29.69% | 29.69% | 35% | 4% | 0.4157% | 0.4157%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-10-01 | 33.2% | 33.2% | 35% | 4% | 0.4648% | 0.4648%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-11-01 | 36.57% | 36.57% | 35% | 4% | 0.512% | 0.512%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2017-12-01 | 68% | 76.62% | 35% | 4% | 0.952% | 1.073%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-01-01 | 77.46% | 77.81% | 35% | 4% | 1.084% | 1.089%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-02-01 | 78.51% | 78.86% | 35% | 4% | 1.099% | 1.104%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-03-01 | 79.35% | 92.12% | 35% | 4% | 1.111% | 1.29%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-04-01 | 92.97% | 92.97% | 35% | 4% | 1.302% | 1.302%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-05-01 | 92.97% | 94.53% | 35% | 4% | 1.302% | 1.323%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-06-01 | 93.76% | 95.32% | 35% | 4% | 1.313% | 1.334%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-07-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-08-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-09-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-10-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-11-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%
EIA | D | EIA Development (Assembly by KP) | D6 | Review by technical counterparts | 2018-12-01 | 100% | 100% | 35% | 4% | 1.4% | 1.4%

## DB Sections
Progress | Section | Section Name | Item | Item Name | Month | Plan Local | Forecast Local | Section Weight | Item Weight | Plan Local | Forecast Local
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-05-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-06-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-07-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-08-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-09-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-10-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-11-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2016-12-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-01-01 | 0% | 0% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-02-01 | 9.901% | 7.985% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-03-01 | 68.3% | 58.46% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-04-01 | 79.11% | 67.13% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-05-01 | 87.76% | 71.19% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-06-01 | 95.36% | 82.99% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-07-01 | 100% | 97.69% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-08-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-09-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-10-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-11-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2017-12-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-01-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-02-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-03-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-04-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-05-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-06-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-07-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-08-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-09-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-10-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-11-01 | 100% | 100% | 10% | 10%
EIA | A | NuevaUnión - Key Decisions | A | NuevaUnión - Key Decisions | 2018-12-01 | 100% | 100% | 10% | 10%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-05-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-06-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-07-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-08-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-09-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-10-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-11-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2016-12-01 | 0% | 0% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-01-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-02-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-03-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-04-01 | 4% | 4% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-05-01 | 38.5% | 38.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-06-01 | 41% | 41% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-07-01 | 43.5% | 43.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-08-01 | 50% | 50% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-09-01 | 52.5% | 52.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-10-01 | 55% | 55% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-11-01 | 57.5% | 57.5% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2017-12-01 | 60% | 60% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-01-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-02-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-03-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-04-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-05-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-06-01 | 92% | 92% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-07-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-08-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-09-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-10-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-11-01 | 100% | 100% | 20% | 20%
EIA | B | Baseline gathering, monitoring and similar | B | Baseline gathering, monitoring and similar | 2018-12-01 | 100% | 100% | 20% | 20%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-05-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-06-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-07-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-08-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-09-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-10-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-11-01 | 0% | 0% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2016-12-01 | 0.8505% | 0.9309% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-01-01 | 1.998% | 2.467% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-02-01 | 6.652% | 5.914% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-03-01 | 23.31% | 21.84% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-04-01 | 61.9% | 38.35% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-05-01 | 79.97% | 69.88% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-06-01 | 93.5% | 84.68% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-07-01 | 99.74% | 97.14% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-08-01 | 99.74% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-09-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-10-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-11-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2017-12-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-01-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-02-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-03-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-04-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-05-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-06-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-07-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-08-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-09-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-10-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-11-01 | 100% | 100% | 35% | 35%
EIA | C | Fluor engineering and NU's input for EIA | C | Fluor engineering and NU's input for EIA | 2018-12-01 | 100% | 100% | 35% | 35%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-05-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-06-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-07-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-08-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-09-01 | 0% | 0% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-10-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-11-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2016-12-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-01-01 | 1.524% | 1.524% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-02-01 | 1.774% | 1.774% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-03-01 | 2.844% | 2.844% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-04-01 | 4.956% | 4.956% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-05-01 | 7.537% | 7.537% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-06-01 | 11.83% | 11.83% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-07-01 | 15.3% | 15.3% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-08-01 | 21.7% | 21.7% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-09-01 | 29.69% | 29.69% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-10-01 | 33.2% | 33.2% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-11-01 | 36.57% | 36.57% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2017-12-01 | 68% | 76.62% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-01-01 | 77.46% | 77.81% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-02-01 | 78.51% | 78.86% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-03-01 | 79.35% | 92.12% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-04-01 | 92.97% | 92.97% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-05-01 | 92.97% | 94.53% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-06-01 | 93.76% | 95.32% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-07-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-08-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-09-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-10-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-11-01 | 100% | 100% | 35% | 10%
EIA | D | EIA Development (Assembly by KP) | D | EIA Development (Assembly by KP) | 2018-12-01 | 100% | 100% | 35% | 10%